## project
Project Planner for Links
[6 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | Working Days
 | time axis 2014-05-12 to 2014-07-10
 | time axis 2014-05-12 to 2014-07-10
UI Mockups | 1 | 7
Web App Architectures - Coursera | 1 | 7
Signup/Signin/Oauth/Token | 8 | 2
Plugin Architecture | 8 | 2
Static Plugin | 10 | 1
Links - CRUD + UI* | 10 | 3
Groups - CRUD + UI* | 10 | 3
Search Users | 13 | 1
Tags - CRUD + UI* | 13 | 3
Share to Group | 14 | 2
User Management in Groups | 16 | 2
Group Timeline | 16 | 2
Accept/Reject Group invite | 18 | 2
Homepage - Feeds/Timeline | 18 | 3
Search by tags | 20 | 2
Pagination of Timeline | 21 | 1
Tags Suggestions - Tags CRUD | 22 | 4
Search Groups | 22 | 3
Pagination of Groups | 25 | 1
Share Plugins (Email/Facebook) | 26 | 1
Share Plugins (LinkedIn/Twitter) | 26 | 1
Bookmarklets | 27 | 3
Android App - 1 | 30 | 7
Android App - 2 | 27 | 7
Alternative Datamodels | 30 | 7
Plugins - 1 | 34 | 7
Plugins - 2 | 37 | 7
User Guide | 39 | 2
API Guide | 41 | 2
Plugin Help Guide | 43 | 2
* includes CRUD, REST API &plugin related UI