## project
Project Planner for Links
[7 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
|  | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
| ACTIVITY | START | DURATION | START | DURATION | COMPLETE | Working Days
 | time axis 2014-05-12 to 2014-07-10
 | time axis 2014-05-12 to 2014-07-10
| UI Mockups | 1 | 8
| Web App Architectures - Coursera | 1 | 8
| Signup/Signin/Oauth/Token | 9 | 3
| Plugin Architecture | 9 | 3
| Static Plugin | 12 | 2
| Links - CRUD + UI* | 12 | 4
| Groups - CRUD + UI* | 14 | 4
| Search Users | 16 | 2
| Tags - CRUD + UI* | 18 | 4
| Share to Group | 18 | 3
| User Management in Groups | 22 | 3
| Group Timeline | 21 | 3
24 | Accept/Reject Group invite | 24 | 3
| Homepage - Feeds/Timeline | 25 | 4
| Search by tags | 27 | 3
| Pagination of Timeline | 29 | 2
| Tags Suggestions - Tags CRUD | 30 | 5
| Search Groups | 31 | 4
| Pagination of Groups | 35 | 2
| Share Plugins (Email/Facebook) | 35 | 2
| Share Plugins (LinkedIn/Twitter) | 37 | 2
| Bookmarklets | 37 | 4
| Android App - 1 | 39 | 8
| Android App - 2 | 41 | 8
| Alternative Datamodels | 46 | 8
| Plugins - 1 | 49 | 8
| Plugins - 2 | 54 | 8
| User Guide | 57 | 3
| API Guide | 57 | 3
| Plugin Help Guide | 57 | 3
* includes CRUD, REST API &plugin related UI